Gold’s Gym

Project North Star

Review | Recap

- SOW No. 01 | Phase 0: Completed - https://golds.stackhack.io

- SOW No. 02 | Phase 1 & 2 Combined: https://golds02.stackhack.io/

- SOW No. 03 – 07 | No SOW

SOW No. 02 – Based on feedback from Client we expedited the Strategy work into the Phase 2 work on the decision to move forward with an “Assemble Strategy”.  Phase 2 was focused on the architecture / blueprint of the Tech Stack.

The primary deliverable was to support Golds Gym in the decision making process, architecture the tech stack, evaluate vendors for the RFI short list and deliver the Playbook for the architecture and RFI planning.

There have been two major change requests, 1) not to go into such details on the Customer Experience and mapping of the Customer Experience and 2) Less focus on the Assemble Architecture and to short list the vendor list and get an RFI completed which we added.

April 2026 & May 2026

| DELIVERABLE | DETAILS | STATUS |
| --- | --- | --- |
| Strategy Session at GG HQ | Onsite in Dallas meetings | Done |
| Technology Strategy Report | URL, v1 delivered & v2 finalized | Updating v2 |
| Customer Experience | Mapping User Stories | Started* |
| Member Facing Layer | Review and Recommend | Done |
| Canocical Data Model | Developed Tool For Model | Done |
| - Department Inputs | Work with Rick on Inputs – Team | Finalizing |
| Architectural Map | Developed and Designed | Started* |
| Vendor List For RFI / RFP | Meetings & Short List Targets | Done |
| RFP Planning | Developed RFI / RFP | Reviewing |
| Vendor Meetings | Attendance Strategic Meetings | In Process |

*Client Requested Adjustments In The Scope

Project Planning

| Date | Milestone | StackHack Oversight & Deliverables | SOW |
| --- | --- | --- | --- |
| 6/1/2026 | RFI Draft & Vendor Meetings Architecture Map / Data Model | Authors the RFI question set mapped to the weighted scoring rubric; provides the architecture map and canonical data model as the RFI technical baseline. | 2 |
| 6/8/2026 | RFI Finalized Version For GG Deliver Version 2 – PDF / Excel | Provides the final RFI packet (PDF + scoring workbook); recommends data-ownership, open-API, and exit / migration clauses as vendor non-negotiables. | 2 |
| 6/15/2026 | RFI Document Dept Additions | Supports Rick and the department teams in gathering inputs; helps fold the additions into the RFI requirement matrix. | 2 |
| -6/19/2026 | -Issue RFI to Selected Vendors | Supports RFI issuance; provides the shared evaluation tracker and scoring framework for the team to use. | 2 |
| 6/22/2026 | Vendor Deep Dives ¦ Demos SOW No. 02 Presentation Finalized | Attends vendor demos, Q&A’s, etc.; provides the finalized SOW No. 02 readout. | 3 |
| 6/29/2026 | Vendor Deep Dives ¦ Demos | Attends vendor demos, Q&A’s, etc. | 3 |
| -Week | RFI Q&A with Vendors | Available in a supporting role for vendor Q&A — advisory and technical input as needed. | 3 |
| 7/6/2026 | Vendor Deep Dives ¦ Demos | Attends additional demos; helps track gaps against the requirements scorecard. | 3 |
| -Week | RFI Q&A with Vendors | Provides technical support on vendor clarifications; helps assess API and integration claims. | 3 |
| -7/10/2026 | -RFI Due From Vendors | Supports review of incoming vendor responses; normalizes them for scoring. | 3 |
| 7/13/2026 | Vendor Deep Dives ¦ Demos RFI Reviews ¦ Analysis ¦ Rubric | Scores responses against the weighted rubric; flags non-negotiable failures. | 3 |
| 7/20/2026 | Vendor Deep Dives ¦ Demos RFI Reviews ¦ Analysis ¦ Rubric Run Via AI Moel – Scoring System | Provides the AI-assisted scoring model for apples-to-apples comparison; delivers the ranked scorecard as input. | 3 |
| 7/27/2026 | Post Decision Next Step Planning Internal RFI Decision/Analysis Mtg | Supports the internal decision meeting; provides the finalist comparison and a recommendation memo as input. | 3 |
| 8/3/2026 –1 | Finalist – Pros ¦ Cons ¦ Risk DD | Provides a finalist due-diligence pack as input: pros / cons, risk register, reference checks, and TCO model. | 3 |
| -8/5/2026 | -GG Vendor Decision | Supports the decision gate; helps document the selection rationale for board and franchise leadership. | 3 |
| 8/10/2026 –2 | Price Negotiation ¦ Due Diligence | Provides advisory support on commercial negotiation — ~400-location leverage and pricing benchmarks against market ranges. | 3 |
| 8/17/2026 –3 | Term Negotiation ¦ Agreement(s) | Provides advisory review of contract terms — SLAs, data ownership, exit / migration, and integration commitments. | 3 |
| 8/24/2026 –4 | GG North Star Presentation | Co-develops the North Star presentation; translates selections into the unified-platform narrative. | 3 |
| 8/31/2026 | Communication to Stakeholders | Supports stakeholder communications; provides input on messaging aligned to the governance and rollout model. | 3 |
| 9/7/2026 | Presentation to Franchisees | Supports the franchisee presentation; helps position platform value and the adoption path. | 3 |
| FUTURE | Implementation Phase | SOW No. 04+ — implementation support: PMO and integration oversight, data-layer build, migration / cutover runbooks, and vendor SLA governance. | 4 |

StackHack operates in an advisory and supporting role throughout — Gold's leads each milestone. The SOW column maps each item: SOW 02 (in progress), proposed SOW 03 (vendor selection through build kickoff), and SOW 04 (implementation).